JOB PORTAL PLATFORM

PROJECT DEVELOPMENT PLAN

45-Day Phased Execution Roadmap

| Version 1.0.0 | Timeline 45 Days |
| --- | --- |
| Project Type Job Portal Web App | Total Phases 5 Phases |

# 1. Project Overview

This document defines the complete development roadmap for a Job Portal Platform modeled. The platform will connect job seekers with employers through a feature-rich, scalable web application delivered within 45 days across five structured development phases.

## 1.1  Project Objectives

- Build a full-featured job portal with separate portals for Job Seekers and Employers

- Deliver a production-ready MVP within 45 calendar days

- Ensure mobile-responsive design and SEO-optimized architecture

- Deploy to cloud infrastructure with CI/CD pipeline and monitoring

## 1.2  Target Users

- Job Seekers: Individuals searching for employment opportunities, able to create profiles, upload resumes, and apply to jobs

- Employers / Recruiters: Companies and HR professionals posting job openings, reviewing applications, and managing hiring pipelines

- Admin: Platform administrators managing users, content moderation, subscription plans, and analytics

# 2. Technology Stack

The platform will be built using a modern, scalable technology stack optimized for performance, developer productivity, and long-term maintainability.

| Layer | Technology | Purpose |
| --- | --- | --- |
| Frontend | React.js | UI components, SSR, routing, SEO optimization |
| Styling | CSS | Responsive design, component library |
| Backend | Node.js + Express.js | REST API, middleware, business logic |
| Database | MySQL | User data, job listings, applications storage |
| Auth | JWT | Secure login, Google/LinkedIn sign-in |
| Storage | Server | Resume uploads, profile images |
| Search | Elasticsearch | Full-text search, job filtering |
| Email | Nodemailer | Verification, alerts, notifications |
| Deployment | Server | Production hosting, load balancing, SSL |
| CI/CD | GitHub Actions | Automated testing and deployment pipeline |

# 3. Master Timeline Overview

The 45-day development cycle is divided into 5 clearly defined phases. Each phase builds upon the previous one, with milestones and deliverables defined at each stage.

| Phase | Phase Name | Timeline | Duration | Status |
| --- | --- | --- | --- | --- |
| 1 | Planning & Setup | Day 1–7 | 7 Days | Planned |
| 2 | Core Backend Development | Day 8–18 | 11 Days | Planned |
| 3 | Frontend Development | Day 19–30 | 12 Days | Planned |
| 4 | Advanced Features & Integration | Day 31–40 | 10 Days | Planned |
| 5 | Testing, QA & Deployment | Day 41–45 | 5 Days | Planned |

Important Note: All phases include daily standups (15 min), end-of-phase code reviews, and documented handoff reports. Buffer days are built into each phase for unforeseen blockers. Any scope changes must go through a change request process.

4. Development Phases — Detailed Breakdown

| PHASE 1 | Project Planning & Environment Setup | ⏱ Day 1 – 7 (7 Days) |
| --- | --- | --- |

This foundational phase establishes the project infrastructure, architectural decisions, and development environment. No feature code is written until all foundations are solid.

## 4.1  Phase 1 Goals

- Finalize all technical and functional requirements

- Set up version control, project management, and communication tools

- Design database schema and define all API contracts

- Create wireframes and UI/UX design system

- Set up local development environments for all team members

## 4.2  Phase 1 Tasks

| # | Task / Feature | Description | Priority | Est. Days |
| --- | --- | --- | --- | --- |
| 1 | Requirements Gathering | Finalize functional & non-functional requirements with stakeholders | CRITICAL | 1–2 |
| 2 | System Architecture Design | Define microservices vs monolith, API structure, DB choice | CRITICAL | 1–2 |
| 3 | Database Schema Design | ERD for Users, Jobs, Applications, Companies, Subscriptions | HIGH | 2–3 |
| 4 | API Contract Definition | Define all REST endpoints with request/response formats in Postman | HIGH | 3–4 |
| 5 | UI/UX Wireframes | Figma wireframes for all major screens (Home, Search, Profile, Dashboard) | HIGH | 3–5 |
| 6 | Dev Environment Setup | Docker, Node.js, React, DB setup for all developers | HIGH | 4–5 |
| 7 | Project Management Setup | JIRA/Trello board, GitHub repo, branch strategy, CI skeleton | MEDIUM | 5–6 |
| 8 | Design System Creation | Color palette, typography, component library scaffolding in Figma | MEDIUM | 6–7 |
| 9 | Phase 1 Review & Sign-off | Stakeholder review of all deliverables and approval to proceed | CRITICAL | 7 |

## 4.3  Phase 1 Deliverables

- Signed-off Requirements Document (SRS)

- System Architecture Diagram

- Complete Database ERD

- Postman API Collection with all endpoint contracts

- Figma Wireframes for all screens

- Configured GitHub repository with branch protection rules

- Functional local dev environment for all team members

| PHASE 2 | Core Backend Development | ⏱ Day 8 – 18 (11 Days) |
| --- | --- | --- |

The backend phase builds the entire server-side logic, database models, authentication system, and all core APIs. All APIs must be tested and documented before the frontend phase begins.

## 4.4  Phase 2 Goals

- Build production-grade REST API for all core platform features

- Implement secure authentication and authorization system

- Create database models and all CRUD operations

- Implement file upload, search, and notification services

- Achieve 80%+ unit test coverage on all API endpoints

## 4.5  Phase 2 Tasks

| # | Task / Feature | Description | Priority | Est. Days |
| --- | --- | --- | --- | --- |
| 1 | Authentication System | JWT auth, refresh tokens, password hashing (bcrypt), session management | CRITICAL | 8–9 |
| 2 | OAuth Integration | Google & LinkedIn OAuth 2.0 sign-in for both job seekers and employers | HIGH | 9–10 |
| 3 | User Management APIs | Register, login, profile CRUD, role-based access (Seeker/Employer/Admin) | CRITICAL | 8–10 |
| 4 | Job Posting APIs | Create/Edit/Delete jobs, job status management, bulk job upload via CSV | CRITICAL | 10–12 |
| 5 | Job Search & Filter API | Full-text search, filters (location, salary, experience, type), pagination, sorting | CRITICAL | 11–13 |
| 6 | Application Management API | Apply to job, track status (Applied/Reviewed/Shortlisted/Rejected) | HIGH | 12–14 |
| 7 | Resume Upload Service | PDF/DOCX upload to AWS S3, parsing with resume parser library | HIGH | 13–15 |
| 8 | Company Profile APIs | Company registration, profile management, logo upload, employee count | HIGH | 14–15 |
| 9 | Email Notification Service | Transactional emails: OTP, application alerts, job alerts via SendGrid | HIGH | 15–16 |
| 10 | Admin APIs | User management, job moderation, platform analytics, subscription management | MEDIUM | 16–17 |
| 11 | API Testing & Documentation | Full test suite with Jest, Postman collection update, Swagger docs | CRITICAL | 17–18 |

## 4.6  Core Data Models

- User Model: id, name, email, password_hash, role (seeker/employer/admin), phone, location, created_at, updated_at

- Job Model: id, title, company_id, description, requirements, salary_range, location, job_type, experience_level, skills[], status, posted_at, expires_at

- Application Model: id, job_id, seeker_id, resume_url, cover_letter, status, applied_at, updated_at

- Company Model: id, name, logo_url, website, industry, size, location, description, verified, recruiter_ids[]

- Resume Model: id, user_id, file_url, parsed_data (JSON), skills[], experience[], education[], last_updated

## 4.7  Phase 2 Deliverables

- Fully functional REST API with all endpoints

- Swagger/OpenAPI documentation

- Jest test suite with 80%+ coverage report

- Database migration scripts

- Deployed backend on staging server

| PHASE 3 | Frontend Development | ⏱ Day 19 – 30 (12 Days) |
| --- | --- | --- |

The frontend phase translates all wireframes and designs into a fully functional, responsive React/Next.js application. This phase focuses on pixel-perfect implementation, performance, and seamless API integration.

## 4.8  Phase 3 Goals

- Build all user-facing pages for Job Seekers and Employers

- Implement state management and API integration layer

- Ensure fully responsive design across all device sizes

- Implement SEO optimization with Next.js SSR/SSG

- Achieve Lighthouse performance score of 85+

## 4.9  Phase 3 Tasks — Job Seeker Portal

| # | Task / Feature | Description | Priority | Est. Days |
| --- | --- | --- | --- | --- |
| 1 | Homepage & Landing Page | Hero search bar, featured jobs, top companies, job categories section | CRITICAL | 19–20 |
| 2 | Job Search Results Page | Filter sidebar, job cards, pagination, sort options, save job toggle | CRITICAL | 20–21 |
| 3 | Job Detail Page | Full JD, company info, apply button, similar jobs, share functionality | CRITICAL | 21–22 |
| 4 | Seeker Registration & Login | Signup form, login, OTP verification, social login buttons | CRITICAL | 19–20 |
| 5 | Seeker Profile Dashboard | Profile completeness meter, edit personal info, work experience, education | HIGH | 22–24 |
| 6 | Resume Upload & Builder | Upload existing resume, basic resume builder form, preview | HIGH | 23–25 |
| 7 | My Applications Page | Application tracker with status badges, job bookmarks, applied history | HIGH | 24–25 |
| 8 | Job Alerts Setup | Email/in-app alert preferences by keyword, location, industry | MEDIUM | 25–26 |

## 4.10  Phase 3 Tasks — Employer Portal

| # | Task / Feature | Description | Priority | Est. Days |
| --- | --- | --- | --- | --- |
| 1 | Employer Registration & Login | Company signup, domain verification, contact person details | CRITICAL | 19–20 |
| 2 | Recruiter Dashboard | Overview stats: active jobs, total applicants, shortlisted, views | CRITICAL | 21–22 |
| 3 | Post a Job Form | Multi-step form: job details, requirements, skills, salary, deadline | CRITICAL | 22–23 |
| 4 | Manage Jobs Page | List active/closed/draft jobs, edit/clone/close actions, job analytics | HIGH | 23–24 |
| 5 | Applicant Management | Per-job applicant list, view resume, update status, add notes, shortlist | HIGH | 24–26 |
| 6 | Company Profile Page | Public company page with branding, about, jobs, reviews section | HIGH | 25–26 |
| 7 | Candidate Search Page | Search job seekers by skills, experience, location with filters | MEDIUM | 26–27 |

## 4.11  Phase 3 Tasks — Common & Admin

| # | Task / Feature | Description | Priority | Est. Days |
| --- | --- | --- | --- | --- |
| 1 | Admin Dashboard | User management, job moderation queue, platform metrics, charts | HIGH | 27–28 |
| 2 | Notification Center | In-app notification bell with real-time updates, mark as read | MEDIUM | 27–28 |
| 3 | Responsive Design Polish | Mobile/tablet breakpoints for all pages, touch-friendly interactions | HIGH | 28–29 |
| 4 | SEO & Performance | Meta tags, sitemap.xml, robots.txt, image optimization, lazy loading | HIGH | 29–30 |
| 5 | Error Pages & Loading States | 404/500 pages, skeleton loaders, empty states, toast notifications | MEDIUM | 29–30 |

## 4.12  Phase 3 Deliverables

- Fully functional frontend application with all pages

- Complete API integration with backend services

- Responsive design verified on mobile, tablet, and desktop

- Lighthouse audit report (target: 85+ score)

- Storybook component library documentation

| PHASE 4 | Advanced Features & Third-Party Integrations | ⏱ Day 31 – 40 (10 Days) |
| --- | --- | --- |

This phase adds the premium features that differentiate the platform: advanced search, subscription/payments, analytics, recommendation engine, and all third-party integrations.

## 4.13  Phase 4 Tasks

| # | Task / Feature | Description | Priority | Est. Days |
| --- | --- | --- | --- | --- |
| 1 | Advanced Search & Elasticsearch | Full-text indexing, auto-suggest, keyword highlighting, saved searches | CRITICAL | 31–33 |
| 2 | Payment Gateway Integration | Razorpay/Stripe for employer subscription plans (Free/Pro/Enterprise) | HIGH | 31–33 |
| 3 | Subscription Plan Management | Plan features gating, job post limits, featured listing, invoice generation | HIGH | 33–34 |
| 4 | AI Job Recommendations | ML-based recommendations using seeker profile, past applications, skills match | HIGH | 33–35 |
| 5 | Resume Parser Integration | Auto-extract skills/experience from uploaded PDFs using parsing API | HIGH | 34–35 |
| 6 | Real-Time Notifications | Socket.io for live notifications: application updates, new job alerts | MEDIUM | 35–36 |
| 7 | Analytics Dashboard (Employer) | Job views, click-through rates, application funnel, heatmaps | MEDIUM | 36–37 |
| 8 | Platform Analytics (Admin) | Total users, DAU/MAU, top companies, top job categories, revenue | MEDIUM | 36–37 |
| 9 | Social Sharing Features | Share jobs on LinkedIn, Twitter, WhatsApp with OG image generation | LOW | 37–38 |
| 10 | LinkedIn Profile Import | Import seeker profile data from LinkedIn API on registration | MEDIUM | 38–39 |
| 11 | SMS Notifications | Twilio SMS for application status updates and OTP verification | MEDIUM | 38–39 |
| 12 | Performance Optimization | Redis caching for search results, DB query optimization, CDN setup | HIGH | 39–40 |

## 4.14  Subscription Plan Structure

| Feature | Free | Pro | Enterprise |
| --- | --- | --- | --- |
| Job Posts / Month | 3 | 20 | Unlimited |
| Featured Listings | No | 5/month | Unlimited |
| Candidate Search | No | Yes | Yes + Advanced Filters |
| Analytics Dashboard | Basic | Full | Full + Export |
| Resume Database Access | No | 100/month | Unlimited |
| Priority Support | No | Email | Dedicated Manager |

| PHASE 5 | Testing, Quality Assurance & Deployment | ⏱ Day 41 – 45 (5 Days) |
| --- | --- | --- |

The final phase ensures the platform is production-ready through comprehensive testing, security audits, performance validation, and a structured deployment process.

## 4.15  Phase 5 Tasks

| # | Task / Feature | Description | Priority | Est. Days |
| --- | --- | --- | --- | --- |
| 1 | End-to-End Testing | Cypress E2E tests covering all critical user flows for both portals | CRITICAL | 41–42 |
| 2 | Unit & Integration Testing | Final review of test suite, fixing failing tests, coverage report | CRITICAL | 41 |
| 3 | Security Audit | OWASP Top 10 checks: SQL injection, XSS, CSRF, rate limiting, headers | CRITICAL | 41–42 |
| 4 | Performance Testing | Load testing with k6/JMeter, optimize bottlenecks, CDN configuration | HIGH | 42–43 |
| 5 | Cross-Browser Testing | Chrome, Firefox, Safari, Edge on desktop + iOS/Android mobile | HIGH | 42 |
| 6 | UAT (User Acceptance Testing) | Stakeholder testing session, bug fixes from feedback | CRITICAL | 43 |
| 7 | Production Deployment | AWS EC2 setup, Nginx config, SSL cert, domain DNS, env variables | CRITICAL | 43–44 |
| 8 | CI/CD Pipeline Finalization | GitHub Actions: auto-test on PR, auto-deploy on merge to main | HIGH | 44 |
| 9 | Monitoring & Logging Setup | AWS CloudWatch / Datadog alerts, error tracking with Sentry | HIGH | 44 |
| 10 | Go-Live & Handoff | Final checks, DNS propagation, smoke testing, documentation handoff | CRITICAL | 45 |

## 4.16  Testing Checklist

- Functional Testing: All 150+ user stories verified against acceptance criteria

- Security Testing: OWASP Top 10, input sanitization, auth bypass attempts, API rate limiting

- Performance Testing: Page load < 3s, API response < 500ms under 500 concurrent users

- Accessibility: WCAG 2.1 AA compliance, keyboard navigation, screen reader support

- SEO Validation: All pages have meta tags, canonical URLs, sitemap indexed in GSC

# 5. Team Roles & Responsibilities

| Role | Active Phases | Key Responsibilities |
| --- | --- | --- |
| Project Manager | All Phases | Sprint planning, stakeholder communication, risk management, timeline tracking, daily standups |
| UI/UX Designer | Phase 1, 3, 5 | Wireframes, design system, Figma prototypes, design reviews, handoff to dev |
| Backend Developer (x2) | Phase 2, 4, 5 | REST API development, database design, authentication, integrations, performance |
| Frontend Developer (x2) | Phase 3, 4, 5 | React/Next.js pages, API integration, responsive design, state management |
| Full-Stack Developer | Phase 2–5 | Cross-stack features, admin panel, real-time features, debugging |
| QA Engineer | Phase 1 (planning), 5 | Test plan creation, manual & automated testing, bug reporting, regression |
| DevOps Engineer | Phase 1, 5 | Infrastructure setup, CI/CD pipelines, monitoring, deployment, cloud config |

# 6. Risk Register

| Risk | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Scope creep from stakeholder change requests | High | High | Formal change request process; freeze scope after Phase 1 sign-off |
| Key developer unavailability / attrition | Medium | High | Cross-training, documentation, 1 backup resource identified per role |
| Third-party API failures (LinkedIn, Payment) | Low | Medium | Mock fallbacks, multiple provider options, sandbox testing first |
| Performance bottlenecks under load | Medium | High | Load testing in Phase 5; Redis caching implemented in Phase 4 |
| Security vulnerabilities in auth system | Low | Critical | OWASP audit in Phase 5; security review after Phase 2 backend complete |
| Timeline delay in Phase 3 (frontend complexity) | Medium | Medium | 1-day buffer per sprint; deprioritize low-priority features if behind |

# 7. Success Metrics & KPIs

## 7.1  Technical KPIs

- API Response Time: P95 < 500ms for all endpoints under normal load

- Uptime SLA: 99.5% availability in production (monitored via CloudWatch)

- Page Load Speed: Lighthouse Performance score > 85 on all major pages

- Test Coverage: Minimum 80% unit test coverage on backend, 70% frontend

- Security: Zero critical vulnerabilities in OWASP audit report

## 7.2  Business KPIs (Post-Launch — 30 Days)

- User Registrations: Target: 500+ registered users within 30 days

- Job Postings: Target: 200+ active job listings from 20+ companies

- Applications Submitted: Target: 1,000+ job applications submitted

- Employer Conversion: Target: 15% of registered employers upgrade to Pro plan

# 8. Assumptions & Constraints

## 8.1  Assumptions

- A team of 6–8 developers is available and dedicated for the full 45 days

- Stakeholder feedback is provided within 24 hours of deliverable submission

- Third-party API credentials (Google, LinkedIn, Razorpay) will be provided by Day 5

- Cloud infrastructure (AWS account, domain name) is provisioned before Phase 5

- Design assets and brand guidelines are finalized and approved by end of Phase 1

## 8.2  Out of Scope (v1.0)

- Native mobile application (iOS/Android) — planned for v2.0

- Video interview module — post-launch feature

- AI-powered chatbot / conversational job matching

- Multi-language support (English-only for v1.0)

- Third-party HR software integrations (ATS, SAP, Workday)

Document Control This document is version 1.0 and is intended for internal project stakeholders only. All phases, timelines, and features are subject to change via formal change request. For queries, contact the Project Manager.